## 0. Guidance & Instructions
MANUAL TESTING DOCUMENTATION GUIDE
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## 1. Test Plan
TEST PLAN
Project Name: | Selenium Python Advanced Capstone Project – Notes App
Test Plan ID: | TP-001
Version: | 1.0
Date: | 06-05-2026
Prepared By: | Maredi Lahari
Approved By:
SCOPE
Features to be Tested:
1.User login functionality via UI
2.Note creation via UI
3.Validation of note visibility
4.API functionality including Login, GET /notes, and DELETE /notes
5.Validating Notes created through UI appearance in API
6.Validating Notes deletion via API
7.Checking UI syncronization after notes deletion through API
8.Validate API response time must be less than 2seconds
9.Negative Scenarios for UI & API
TESTING TYPE
Functional Testing | ✓
Regression Testing | ✓
Integration Testing | ✓
UAT | ✓
TEST ENVIRONMENT
Environment: | QA
Browser/OS: | Chrome / Windows 11
TIMELINE | 3 Days
Start Date: | 2026-05-05
End Date: | 2026-07-05
RESOURCES | UI: https://practice.expandtesting.com/notes/app
QA Lead: | Maredi Lahari
QA Resources: | Pytest,Selenium,Allure,Jenkins
Test Data Provider: | Self-generated test data
Test files,environment.py
RISKS & ASSUMPTIONS
Risks:
1.UI changes may effect test cases
2.Improper authentication token causes errors and block API testing
3.Network issues delays response time
Assumptions:
1.Assuming application is stable and accessible in QA environment.
2. API endpoints are working correctly.
3. Test environment is available throughout testing.

## 2. Test Scenarios
Scenario ID | Scenario Name | Description | Pre-conditions
TS-01 | Validate UI Login | Verify user login with valid credentials | User account should exist
TS-02 | Create Note via UI | Verify note creation through UI | User logged into application
TS-03 | Validate Instant UI Update | Verify created note appears instantly in UI list | User logged into notes dashboard
TS-04 | Validate GET /notes API | Verify GET /notes returns all notes with status 200 | Valid API token available
TS-05 | Validate UI to API Sync | Verify UI-created note appears in API response | User logged in and API accessible
TS-06 | Delete Note via API | Verify note deletion using DELETE API | Note exists in system
TS-07 | Validate API to UI Sync | Verify deleted note disappears from UI | Note exists and user logged into UI
TS-08 | Negative Validation | Verify invalid inputs and API error handling | User is on login page
TS-09 | Create Empty Note | Verify unable to create empty note | User opened create note form
TS-10 | Performance Validation | Verify response time is < 2 seconds | API service is available

## 3. Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result | Priority | Status
TC-UI-01 | TS-01 | Valid Login | User exists | Open app → Enter valid creds → Login | Login success | High | Pass
TC-UI-02 | TS-02 | Create Note | Logged in | Enter title/desc → Save | Note saved | High | Pass
TC-UI-02A | TS-03 | Create Empty Note | Logged in | Leave fields empty → Save | Validation error | High | Pass
TC-API-01 | TS-04 | GET Notes | API auth | Send GET /notes | 200 + list | High | Pass
TC-E2E-01 | TS-05 | UI→API Sync | Logged in | Create note → Call API → Compare | Data matches | High | Pass
TC-API-02 | TS-06 | Delete Note | Note exists | DELETE /notes/id | Deleted | High | Pass
TC-E2E-02 | TS-07 | API→UI Sync | Note exists | Delete → Refresh UI | Not visible | High | Pass
TC-API-03 | TS-08 | Performance | API auth | Measure response time | <2 sec | Medium | Pass
TC-NEG-01 | TS-09 | Invalid Login | None | Wrong creds → Login | Error message | High | Pass

## 4. Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid User | E-mail: laharimaredi0103@gmail.com, Password: lahariM3* | Valid login scenarios
TD-002 | Invalid User | 1.E-mail: abcemail@gmail.com, Password: wrongpassword | Negative test cases
2.E-mail : " ",Password : " "
3.E-mail :laharimaredi0103@gmail.com, Password: " "
TD-003 | Empty Credentials | E-mail:" " Password: " " | Negative test cases
TD-004 | Valid Note Data | Title: Daily Tasks Description: Complete testing tasks, review automation scripts, and update reports. Category:"work" | To check Valid note creation and check visibility of notes
TD-005 | Empty Note Data | Title: :"" Description:" " | Invalid Notes Creation Check
TD-006 | Valid API Token | Bearer 276b2949f60c44cc8b1a78e1e2 e3efe13a3e53a185a3404ea5a38e25 5c98ff6 | To authenticate API requests and verify authorized access
TD-007 | Invalid API Token | Bearer 276b2949f60c44cc8b1a78e1e2 | To validate API response for unauthorized access
TD-008 | Valid Note ID | 69fb80bd81124e02985b9c98 | To verify deletion of note using API
TD-009 | Invalid Endpoint | https://practice.expandtesting.com/notes /api/users/logins | To validate API behavior for incorrect endpoint

## 5. Test Execution
Test Case ID | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Remarks
TC-UI-01 | Cycle-1 | Login with valid credentials | Maredi Lahari | 06-05-2026 | Pass | Executed successfully
TC-UI-02 | Cycle-1 | Create note through UI | Maredi Lahari | 06-05-2026 | Pass | Note created successfully
TC-UI-03 | Cycle-1 | Validate note instantly appears in UI | Maredi Lahari | 06-05-2026 | Pass | UI updated instantly
TC-API-01 | Cycle-1 | Validate GET /notes API response | Maredi Lahari | 06-05-2026 | Pass | Status 200 received
TC-E2E-01 | Cycle-1 | Validate UI note available in API | Maredi Lahari | 06-05-2026 | Pass | UI and API data matched
TC-API-02 | Cycle-1 | Delete note using API | Maredi Lahari | 06-05-2026 | Pass | Note deleted successfully
TC-E2E-02 | Cycle-1 | Validate deleted note removed from UI | Maredi Lahari | 06-05-2026 | Pass | Deleted note removed from UI
TC-NEG-01 | Cycle-1 | Validate invalid login | Maredi Lahari | 06-05-2026 | Pass | Validation displayed correctly
TC-NEG-02 | Cycle-1 | Validate invalid API request | Maredi Lahari | 06-05-2026 | Pass | Unauthorized status returned

## 6. Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Test Coverage | Status
FR-01 | TC-UI-01 | UI login should work | Covered | Completed
FR-02 | TC-UI-02 | Create note via UI | Covered | Completed
FR-03 | TC-UI-03 | Note should appear instantly in UI list | Covered | Completed
FR-04 | TC-API-01 | API GET /notes returns list | Covered | Completed
FR-05 | TC-E2E-01 | UI-created note must appear in API | Covered | Completed
FR-06 | TC-API-02 | Delete note via API | Covered | Completed
FR-07 | TC-E2E-02 | Deleted note must disappear from UI | Covered | Completed
FR-08 | TC-API-01 | API response < 2s | Covered | Completed
FR-09 | TC-NEG-01, TC-NEG-02 | Negative scenarios (UI & API) | Covered | Completed

## 7. Defect Report
Defect ID | Test Case ID | Defect Title | Defect Description | Severity | Priority | Status | Assigned To | Found Date | Remarks
DEF-001 | TC-UI-02 | Note creation limit issue | Application does not allow creating new notes after reaching maximum note limit | Medium | High | Open | Developer | 06-05-2026 | Requires note limit handling or cleanup
DEF-001 | TC-NEG-01 | Validation delay | Error message displayed with slight delay | Low | Low | Closed | Developer | 06-05-2026 | Fixed successfully

## 8. Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name: | Notes Application Testing
Test Cycle: | Cycle-1
Report Date: | 06-05-2026
Prepared By: | Maredi Lahari
EXECUTION SUMMARY
Total Test Cases: | 15
Test Cases Executed: | 15
Test Cases Passed: | 15
Test Cases Failed: | 0
Pass Percentage: | 100
DEFECT SUMMARY
Total Defects: | 2
Critical Defects: | 0
High Defects: | 0
Medium Defects: | 1
Low Defects: | 1
Open Defects: | 1
Closed Defects: | 1
CONCLUSION
Testing Status: | Completed
Release Readiness: | Ready for Production
Overall Recommendation: | Application is stable and ready for release
REMARKS
All test cases executed successfully. Application is stable. UI and API functionalities are working correctly. Data synchronization between UI and API is verified and negative scenarios are handled properly.